## Sheet1
UserCode | taskName | HoursWorked | OvertimeWorked | dateOfWork | ProjectJobId | ShiftType | ForemanName | IsVerified | JobName | estimatedHours | TaskId
BENDAN | Penthouse siding and coping | 8 |  | 2024-08-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-08-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Commute to Site | 6 |  | 2024-07-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Garage Gutters | 6 |  | 2024-07-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Paperwork | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | L10 deck panels | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Column wraps @ podium | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Wall panels @ entry vestibule | 3 |  | 2024-07-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Penthouse gutters and DS | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Exterior window installation | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Basement waterproofing | 4 |  | 2024-07-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:8/5/2024 5:07:23 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Elevator shaft framing | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Site drainage installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Concrete foundation pouring | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | HVAC ductwork installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Interior wall framing | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Electrical conduit installation | 2 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Fire sprinkler system installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Roof membrane installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Floor tile installation | 8 |  | 2024-07-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Drywall installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Parking lot asphalt paving | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Landscape irrigation installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Structural steel erection | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Guardrail installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Exterior painting | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Interior door installation | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Window caulking and sealing | 8 |  | 2024-07-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Ceiling grid installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Building insulation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Hardwood flooring installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Crown molding installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Kitchen cabinetry installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Bathroom fixture installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Tool organization | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Team safety meeting | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Material delivery coordination | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Quality control inspection | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Stair railing installation | 8 |  | 2024-07-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Building permit processing | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Demolition work | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Scaffolding assembly | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Masonry wall construction | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Plumbing rough-in | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Exterior lighting installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Rooftop HVAC unit installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Subcontractor coordination | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Balcony waterproofing | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Emergency exit signage installation | 8 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Project planning and scheduling | 4 |  | 2024-07-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
TRACCO | Security system wiring | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Penthouse siding and coping | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Roof screen wall | 6 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Commute to Site | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Garage Gutters | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Paperwork | 7 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | L10 deck panels | 1 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Column wraps @ podium | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Wall panels @ entry vestibule | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Penthouse gutters and DS | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Exterior window installation | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Facade metal panel installation | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Basement waterproofing | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Elevator shaft framing | 8 |  | 2024-07-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/29/2024 5:35:14 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Site drainage installation | 2 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Concrete foundation pouring | 6 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | HVAC ductwork installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Interior wall framing | 7 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Electrical conduit installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Fire sprinkler system installation | 5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Roof membrane installation | 1.5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Floor tile installation | 6.5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Drywall installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Structural steel erection | 2 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Guardrail installation | 6 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Exterior painting | 3 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Interior door installation | 5 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Window caulking and sealing | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Ceiling grid installation | 8 |  | 2024-07-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Building insulation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Hardwood flooring installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Crown molding installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Kitchen cabinetry installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Tool organization | 2 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Team safety meeting | 6 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Material delivery coordination | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Quality control inspection | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Stair railing installation | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building permit processing | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Demolition work | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Scaffolding assembly | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Masonry wall construction | 8 |  | 2024-07-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Plumbing rough-in | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Exterior lighting installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Rooftop HVAC unit installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Subcontractor coordination | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Curtain wall installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Balcony waterproofing | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Emergency exit signage installation | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Project planning and scheduling | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Security system wiring | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Penthouse siding and coping | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Roof screen wall | 5 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Commute to Site | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Garage Gutters | 8 |  | 2024-07-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Paperwork | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | L10 deck panels | 6 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Column wraps @ podium | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Wall panels @ entry vestibule | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Penthouse gutters and DS | 2 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Sheet metal roof @ L14 canopy (roof build up) | 6 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Exterior window installation | 7.5 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Facade metal panel installation | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Basement waterproofing | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Elevator shaft framing | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Site drainage installation | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Concrete foundation pouring | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | HVAC ductwork installation | 8 |  | 2024-07-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Interior wall framing | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Electrical conduit installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Fire sprinkler system installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Roof membrane installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Floor tile installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Drywall installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Structural steel erection | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Guardrail installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Exterior painting | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Interior door installation | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Window caulking and sealing | 8 |  | 2024-07-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/19/2024 4:33:05 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Ceiling grid installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Building insulation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Hardwood flooring installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Crown molding installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Kitchen cabinetry installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Tool organization | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Team safety meeting | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Material delivery coordination | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Quality control inspection | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Stair railing installation | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building permit processing | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Demolition work | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Scaffolding assembly | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Masonry wall construction | 8 |  | 2024-07-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Plumbing rough-in | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Exterior lighting installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Rooftop HVAC unit installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Subcontractor coordination | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Curtain wall installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Balcony waterproofing | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Emergency exit signage installation | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Project planning and scheduling | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Security system wiring | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Penthouse siding and coping | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Roof screen wall | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Commute to Site | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Garage Gutters | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Paperwork | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | L10 deck panels | 8 |  | 2024-07-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Column wraps @ podium | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Wall panels @ entry vestibule | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Penthouse gutters and DS | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Exterior window installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Facade metal panel installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Basement waterproofing | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Elevator shaft framing | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Site drainage installation | 7.5 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Concrete foundation pouring | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | HVAC ductwork installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Interior wall framing | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Electrical conduit installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Fire sprinkler system installation | 8 |  | 2024-07-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Roof membrane installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Floor tile installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Drywall installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Parking lot asphalt paving | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Landscape irrigation installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Structural steel erection | 2 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Guardrail installation | 6 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Exterior painting | 7.5 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Interior door installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Window caulking and sealing | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building insulation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Hardwood flooring installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Crown molding installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Kitchen cabinetry installation | 8 |  | 2024-07-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GOETRO | Bathroom fixture installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Tool organization | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Team safety meeting | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Material delivery coordination | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Quality control inspection | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Stair railing installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Building permit processing | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Demolition work | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Scaffolding assembly | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Masonry wall construction | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Plumbing rough-in | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Exterior lighting installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Rooftop HVAC unit installation | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Subcontractor coordination | 8 |  | 2024-07-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/13/2024 9:46:24 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Curtain wall installation | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Balcony waterproofing | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Emergency exit signage installation | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Project planning and scheduling | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Security system wiring | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Penthouse siding and coping | 6 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Roof screen wall | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Commute to Site | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Garage Gutters | 5 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Paperwork | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | L10 deck panels | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Column wraps @ podium | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Wall panels @ entry vestibule | 8 |  | 2024-07-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CARBRA | Penthouse gutters and DS | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Exterior window installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Facade metal panel installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Basement waterproofing | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Elevator shaft framing | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Site drainage installation | 7.5 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Concrete foundation pouring | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | HVAC ductwork installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Roof membrane installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Floor tile installation | 8 |  | 2024-07-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Drywall installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Parking lot asphalt paving | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Landscape irrigation installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Structural steel erection | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Guardrail installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Exterior painting | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Interior door installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Window caulking and sealing | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building insulation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Hardwood flooring installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Crown molding installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Kitchen cabinetry installation | 8 |  | 2024-07-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/8/2024 5:49:01 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Tool organization | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Team safety meeting | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Material delivery coordination | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Quality control inspection | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Stair railing installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building permit processing | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Demolition work | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Scaffolding assembly | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Masonry wall construction | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Plumbing rough-in | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Exterior lighting installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Rooftop HVAC unit installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Subcontractor coordination | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Curtain wall installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Balcony waterproofing | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Emergency exit signage installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Project planning and scheduling | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Security system wiring | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Penthouse siding and coping | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Roof screen wall | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Commute to Site | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Garage Gutters | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Paperwork | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | L10 deck panels | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Column wraps @ podium | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Wall panels @ entry vestibule | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Penthouse gutters and DS | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Exterior window installation | 7 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Facade metal panel installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Basement waterproofing | 7.5 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Elevator shaft framing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Site drainage installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Concrete foundation pouring | 4 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | HVAC ductwork installation | 4 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Interior wall framing | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Electrical conduit installation | 2 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Fire sprinkler system installation | 6 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof membrane installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Floor tile installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Drywall installation | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Parking lot asphalt paving | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Landscape irrigation installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Structural steel erection | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Guardrail installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Exterior painting | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Interior door installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Window caulking and sealing | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Ceiling grid installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Building insulation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Hardwood flooring installation | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Crown molding installation | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Kitchen cabinetry installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Bathroom fixture installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Tool organization | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Team safety meeting | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Material delivery coordination | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Quality control inspection | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Stair railing installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Building permit processing | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Demolition work | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Scaffolding assembly | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Masonry wall construction | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Plumbing rough-in | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Exterior lighting installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Rooftop HVAC unit installation | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Subcontractor coordination | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:7/1/2024 5:49:52 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Emergency exit signage installation | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Project planning and scheduling | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Security system wiring | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-06-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Roof screen wall | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Commute to Site | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Garage Gutters | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Paperwork | 8 |  | 2024-06-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | L10 deck panels | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Column wraps @ podium | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Wall panels @ entry vestibule | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Penthouse gutters and DS | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Exterior window installation | 3 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Facade metal panel installation | 5 |  | 2024-06-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Basement waterproofing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Elevator shaft framing | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Site drainage installation | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Concrete foundation pouring | 8 |  | 2024-06-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/27/2024 9:29:56 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
ATWAVO | HVAC ductwork installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Interior wall framing | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Electrical conduit installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Fire sprinkler system installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Roof membrane installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Floor tile installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Drywall installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Parking lot asphalt paving | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Landscape irrigation installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Structural steel erection | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Guardrail installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Exterior painting | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Interior door installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Window caulking and sealing | 6 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Ceiling grid installation | 0.5 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building insulation | 7.5 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Hardwood flooring installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Crown molding installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Kitchen cabinetry installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Bathroom fixture installation | 8 |  | 2024-06-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
ATWAVO | Tool organization | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Team safety meeting | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Material delivery coordination | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Quality control inspection | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Stair railing installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Building permit processing | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Demolition work | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Scaffolding assembly | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Masonry wall construction | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Plumbing rough-in | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Exterior lighting installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Rooftop HVAC unit installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Subcontractor coordination | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Curtain wall installation | 3 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Balcony waterproofing | 5 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Emergency exit signage installation | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Project planning and scheduling | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-06-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
ATWAVO | Commute to Site | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Garage Gutters | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Paperwork | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | L10 deck panels | 3 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Column wraps @ podium | 5 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Wall panels @ entry vestibule | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Penthouse gutters and DS | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Exterior window installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Facade metal panel installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Basement waterproofing | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Elevator shaft framing | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Site drainage installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Concrete foundation pouring | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | HVAC ductwork installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Interior wall framing | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Electrical conduit installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Fire sprinkler system installation | 8 |  | 2024-06-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
ATWAVO | Roof membrane installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Floor tile installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Drywall installation | 3 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Parking lot asphalt paving | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Landscape irrigation installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Structural steel erection | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Guardrail installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Exterior painting | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Interior door installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Window caulking and sealing | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Ceiling grid installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Building insulation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Hardwood flooring installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Crown molding installation | 5 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Kitchen cabinetry installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Bathroom fixture installation | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Tool organization | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Team safety meeting | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Material delivery coordination | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Quality control inspection | 8 |  | 2024-06-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
ATWAVO | Stair railing installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
NGUKHA | Building permit processing | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Demolition work | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Scaffolding assembly | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Masonry wall construction | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Plumbing rough-in | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Exterior lighting installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Rooftop HVAC unit installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Subcontractor coordination | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Curtain wall installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Balcony waterproofing | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Emergency exit signage installation | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Project planning and scheduling | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Security system wiring | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Penthouse siding and coping | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Roof screen wall | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Commute to Site | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Garage Gutters | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Paperwork | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | L10 deck panels | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Column wraps @ podium | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Wall panels @ entry vestibule | 7 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse gutters and DS | 1 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/24/2024 5:31:57 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Exterior window installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Facade metal panel installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Basement waterproofing | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Elevator shaft framing | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Site drainage installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Concrete foundation pouring | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | HVAC ductwork installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Interior wall framing | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Electrical conduit installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Fire sprinkler system installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Roof membrane installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Floor tile installation | 3 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Drywall installation | 5 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Structural steel erection | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Guardrail installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Exterior painting | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Interior door installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Window caulking and sealing | 3 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Ceiling grid installation | 5 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Building insulation | 3 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Hardwood flooring installation | 5 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Crown molding installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Kitchen cabinetry installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Bathroom fixture installation | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Tool organization | 8 |  | 2024-06-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Team safety meeting | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Material delivery coordination | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Quality control inspection | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Stair railing installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Building permit processing | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Demolition work | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Scaffolding assembly | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Masonry wall construction | 7.5 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Plumbing rough-in | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Exterior lighting installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Rooftop HVAC unit installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Subcontractor coordination | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Curtain wall installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Balcony waterproofing | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Emergency exit signage installation | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Project planning and scheduling | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Security system wiring | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Penthouse siding and coping | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Roof screen wall | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Commute to Site | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Garage Gutters | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Paperwork | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | L10 deck panels | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Column wraps @ podium | 8 |  | 2024-06-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Wall panels @ entry vestibule | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Penthouse gutters and DS | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Exterior window installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Facade metal panel installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Basement waterproofing | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Elevator shaft framing | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Site drainage installation | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Concrete foundation pouring | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | HVAC ductwork installation | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Interior wall framing | 4 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Electrical conduit installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Fire sprinkler system installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Roof membrane installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Floor tile installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Drywall installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Parking lot asphalt paving | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Landscape irrigation installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Structural steel erection | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Guardrail installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Exterior painting | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Interior door installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Window caulking and sealing | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Ceiling grid installation | 8 |  | 2024-06-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Building insulation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Hardwood flooring installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Crown molding installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Kitchen cabinetry installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Bathroom fixture installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Tool organization | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Team safety meeting | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Material delivery coordination | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Quality control inspection | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Stair railing installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Building permit processing | 7.5 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Demolition work | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Scaffolding assembly | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Masonry wall construction | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Plumbing rough-in | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Exterior lighting installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Rooftop HVAC unit installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Subcontractor coordination | 3 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Curtain wall installation | 5 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Project planning and scheduling | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-06-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Commute to Site | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Garage Gutters | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Paperwork | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | L10 deck panels | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Column wraps @ podium | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Wall panels @ entry vestibule | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Penthouse gutters and DS | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Exterior window installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Facade metal panel installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Basement waterproofing | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Elevator shaft framing | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Site drainage installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Concrete foundation pouring | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | HVAC ductwork installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Roof membrane installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Floor tile installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Drywall installation | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Parking lot asphalt paving | 8 |  | 2024-06-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/16/2024 6:37:14 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Landscape irrigation installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Structural steel erection | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Guardrail installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Exterior painting | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Interior door installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Window caulking and sealing | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Ceiling grid installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Building insulation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Hardwood flooring installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Crown molding installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Kitchen cabinetry installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Bathroom fixture installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Tool organization | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Team safety meeting | 3 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Material delivery coordination | 5 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Quality control inspection | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Stair railing installation | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Building permit processing | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Demolition work | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Scaffolding assembly | 8 |  | 2024-06-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Masonry wall construction | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Plumbing rough-in | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Exterior lighting installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Rooftop HVAC unit installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Subcontractor coordination | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Curtain wall installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Balcony waterproofing | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Emergency exit signage installation | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Project planning and scheduling | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Security system wiring | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Penthouse siding and coping | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Roof screen wall | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Commute to Site | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Garage Gutters | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Paperwork | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | L10 deck panels | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Column wraps @ podium | 8 |  | 2024-06-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Sheet metal roof @ L14 canopy | 7 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Wall panels @ entry vestibule | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Penthouse gutters and DS | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Exterior window installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Facade metal panel installation | 3 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Basement waterproofing | 5 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Elevator shaft framing | 3 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Site drainage installation | 5 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Concrete foundation pouring | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | HVAC ductwork installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Interior wall framing | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Electrical conduit installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Fire sprinkler system installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Roof membrane installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Floor tile installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Drywall installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Parking lot asphalt paving | 5.25 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Landscape irrigation installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Structural steel erection | 6.5 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Guardrail installation | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Exterior painting | 8 |  | 2024-06-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Interior door installation | 4.5 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Window caulking and sealing | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Ceiling grid installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Building insulation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Hardwood flooring installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Crown molding installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Kitchen cabinetry installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Bathroom fixture installation | 3 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Tool organization | 5 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Team safety meeting | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Material delivery coordination | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Quality control inspection | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Stair railing installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building permit processing | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Demolition work | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Scaffolding assembly | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Masonry wall construction | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Plumbing rough-in | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Exterior lighting installation | 1.75 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Rooftop HVAC unit installation | 8 |  | 2024-06-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Subcontractor coordination | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Curtain wall installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Balcony waterproofing | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Emergency exit signage installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Project planning and scheduling | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Security system wiring | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Penthouse siding and coping | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Roof screen wall | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Commute to Site | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Garage Gutters | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Paperwork | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | L10 deck panels | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Column wraps @ podium | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Wall panels @ entry vestibule | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Penthouse gutters and DS | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Exterior window installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Facade metal panel installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Basement waterproofing | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Elevator shaft framing | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Site drainage installation | 8 |  | 2024-06-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/7/2024 4:41:02 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Concrete foundation pouring | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | HVAC ductwork installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Interior wall framing | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Electrical conduit installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Fire sprinkler system installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Roof membrane installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Floor tile installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Drywall installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Parking lot asphalt paving | 4 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Landscape irrigation installation | 4 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Structural steel erection | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Guardrail installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior painting | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Interior door installation | 5 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Window caulking and sealing | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Ceiling grid installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building insulation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Hardwood flooring installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Crown molding installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Kitchen cabinetry installation | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Bathroom fixture installation | 8 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Tool organization | 10 |  | 2024-05-31 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Team safety meeting | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Material delivery coordination | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Quality control inspection | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Stair railing installation | 2 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Building permit processing | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Demolition work | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Scaffolding assembly | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Masonry wall construction | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Plumbing rough-in | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior lighting installation | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Rooftop HVAC unit installation | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Subcontractor coordination | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Curtain wall installation | 6.5 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Balcony waterproofing | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Project planning and scheduling | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Security system wiring | 8 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Penthouse siding and coping | 10 |  | 2024-05-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Roof screen wall | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Commute to Site | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Garage Gutters | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Paperwork | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | L10 deck panels | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Column wraps @ podium | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Wall panels @ entry vestibule | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Penthouse gutters and DS | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Exterior window installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Facade metal panel installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Basement waterproofing | 8 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Elevator shaft framing | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Site drainage installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Concrete foundation pouring | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | HVAC ductwork installation | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Interior wall framing | 10 |  | 2024-05-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Electrical conduit installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Fire sprinkler system installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Roof membrane installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Floor tile installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Drywall installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Parking lot asphalt paving | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Landscape irrigation installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Structural steel erection | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Guardrail installation | 8 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior painting | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Interior door installation | 7.5 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Window caulking and sealing | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Ceiling grid installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building insulation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Hardwood flooring installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Crown molding installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Kitchen cabinetry installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Bathroom fixture installation | 10 |  | 2024-05-28 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/2/2024 8:31:17 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Tool organization | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Team safety meeting | 6.5 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Material delivery coordination | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Quality control inspection | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Stair railing installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Building permit processing | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Demolition work | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Scaffolding assembly | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Masonry wall construction | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Plumbing rough-in | 5 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior lighting installation | 1.5 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Rooftop HVAC unit installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Subcontractor coordination | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Curtain wall installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Project planning and scheduling | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Security system wiring | 8 |  | 2024-05-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Penthouse siding and coping | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Roof screen wall | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Commute to Site | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Garage Gutters | 1 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Paperwork | 7 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | L10 deck panels | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Column wraps @ podium | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Wall panels @ entry vestibule | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Penthouse gutters and DS | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Exterior window installation | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Basement waterproofing | 8 |  | 2024-05-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Elevator shaft framing | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Site drainage installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Concrete foundation pouring | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | HVAC ductwork installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Interior wall framing | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Electrical conduit installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Fire sprinkler system installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Roof membrane installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Floor tile installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Drywall installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Parking lot asphalt paving | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Landscape irrigation installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Structural steel erection | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Guardrail installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Exterior painting | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Interior door installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Window caulking and sealing | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Ceiling grid installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Building insulation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Hardwood flooring installation | 8 |  | 2024-05-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Crown molding installation | 2 |  | 2024-05-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Kitchen cabinetry installation | 2 |  | 2024-05-21 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Bathroom fixture installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Tool organization | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Team safety meeting | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Material delivery coordination | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Quality control inspection | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Stair railing installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Building permit processing | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Demolition work | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Scaffolding assembly | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Masonry wall construction | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Plumbing rough-in | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior lighting installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Rooftop HVAC unit installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Subcontractor coordination | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Curtain wall installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Balcony waterproofing | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Emergency exit signage installation | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Project planning and scheduling | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Security system wiring | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Penthouse siding and coping | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Roof screen wall | 2.5 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Commute to Site | 8 |  | 2024-05-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/28/2024 4:55:46 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BURAAR | Garage Gutters |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Paperwork |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HENAUS | L10 deck panels |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Column wraps @ podium |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Sheet metal roof @ L14 canopy |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Wall panels @ entry vestibule |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Penthouse gutters and DS |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Sheet metal roof @ L14 canopy (roof build up) |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior window installation |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Facade metal panel installation |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Basement waterproofing |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Elevator shaft framing |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Site drainage installation |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Concrete foundation pouring |  | 8 | 2024-05-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | HVAC ductwork installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Interior wall framing | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Electrical conduit installation | 3 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Fire sprinkler system installation | 5 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Roof membrane installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Floor tile installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Drywall installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Parking lot asphalt paving | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Landscape irrigation installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Structural steel erection | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Guardrail installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Exterior painting | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Interior door installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Window caulking and sealing | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building insulation | 3 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Hardwood flooring installation | 5 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Crown molding installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Kitchen cabinetry installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Bathroom fixture installation | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Tool organization | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Team safety meeting | 8 |  | 2024-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Material delivery coordination | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Quality control inspection | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Stair railing installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Building permit processing | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Demolition work | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Scaffolding assembly | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Masonry wall construction | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Plumbing rough-in | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Exterior lighting installation | 4 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Rooftop HVAC unit installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Subcontractor coordination | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Curtain wall installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Balcony waterproofing | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Emergency exit signage installation | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Project planning and scheduling | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Security system wiring | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Penthouse siding and coping | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Roof screen wall | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Commute to Site | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Garage Gutters | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Paperwork | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | L10 deck panels | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Column wraps @ podium | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Wall panels @ entry vestibule | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Penthouse gutters and DS | 8 |  | 2024-05-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Exterior window installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Facade metal panel installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Basement waterproofing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Elevator shaft framing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Site drainage installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Concrete foundation pouring | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | HVAC ductwork installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Interior wall framing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Electrical conduit installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Fire sprinkler system installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Roof membrane installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Floor tile installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Drywall installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Parking lot asphalt paving | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Landscape irrigation installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Structural steel erection | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Guardrail installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Exterior painting | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Interior door installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Window caulking and sealing | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Ceiling grid installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Building insulation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Hardwood flooring installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Crown molding installation | 8 |  | 2024-05-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Kitchen cabinetry installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Bathroom fixture installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Tool organization | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Team safety meeting | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Material delivery coordination | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Quality control inspection | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Stair railing installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Building permit processing | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Demolition work | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Scaffolding assembly | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Masonry wall construction | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Plumbing rough-in | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Exterior lighting installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Rooftop HVAC unit installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Subcontractor coordination | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Curtain wall installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Balcony waterproofing | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Emergency exit signage installation | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Project planning and scheduling | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-05-14 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUTHAR | Commute to Site | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BENDAN | Garage Gutters | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CHAJAV | Paperwork | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | L10 deck panels | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Column wraps @ podium | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Wall panels @ entry vestibule | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Penthouse gutters and DS | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Exterior window installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Facade metal panel installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Basement waterproofing | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Elevator shaft framing | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Site drainage installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Concrete foundation pouring | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | HVAC ductwork installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Interior wall framing | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Electrical conduit installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Fire sprinkler system installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Roof membrane installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Floor tile installation | 7.5 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Drywall installation | 8 |  | 2024-05-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/20/2024 5:49:26 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BURAAR | Parking lot asphalt paving |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Landscape irrigation installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Structural steel erection |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Guardrail installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Exterior painting |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Interior door installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Window caulking and sealing |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Ceiling grid installation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Building insulation |  | 8 | 2024-05-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Hardwood flooring installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Crown molding installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Kitchen cabinetry installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Bathroom fixture installation | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Tool organization | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Team safety meeting | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Material delivery coordination | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Quality control inspection | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Stair railing installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building permit processing | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Demolition work | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Scaffolding assembly | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Masonry wall construction | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Plumbing rough-in | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Exterior lighting installation | 5 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Rooftop HVAC unit installation | 8 |  | 2024-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Subcontractor coordination | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Curtain wall installation | 3 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Balcony waterproofing | 5 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Emergency exit signage installation | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Project planning and scheduling | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Security system wiring | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Penthouse siding and coping | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Roof screen wall | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Commute to Site | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Garage Gutters | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Paperwork | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | L10 deck panels | 7.75 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Column wraps @ podium | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Wall panels @ entry vestibule | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Penthouse gutters and DS | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Exterior window installation | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Facade metal panel installation | 8 |  | 2024-05-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Basement waterproofing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Elevator shaft framing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Site drainage installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Concrete foundation pouring | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | HVAC ductwork installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Interior wall framing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Electrical conduit installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Fire sprinkler system installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Roof membrane installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Floor tile installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Drywall installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Parking lot asphalt paving | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Landscape irrigation installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Structural steel erection | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Guardrail installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Exterior painting | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Interior door installation | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Window caulking and sealing | 8 |  | 2024-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Ceiling grid installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Building insulation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Hardwood flooring installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Crown molding installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Kitchen cabinetry installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Bathroom fixture installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Tool organization | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Team safety meeting | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Material delivery coordination | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Quality control inspection | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Stair railing installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building permit processing | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Demolition work | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Scaffolding assembly | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Masonry wall construction | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Plumbing rough-in | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Exterior lighting installation | 8 |  | 2024-05-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
PARBRY | Rooftop HVAC unit installation | 7 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SMICHA | Subcontractor coordination | 7 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRECHR | Curtain wall installation | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Balcony waterproofing | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Emergency exit signage installation | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Project planning and scheduling | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Security system wiring | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Penthouse siding and coping | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Roof screen wall | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Commute to Site | 1 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Garage Gutters | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Paperwork | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | L10 deck panels | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Column wraps @ podium | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Wall panels @ entry vestibule | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse gutters and DS | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/12/2024 6:56:05 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
TRACCO | Exterior window installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BURAAR | Facade metal panel installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
UTLJOH | Basement waterproofing |  | 6 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Elevator shaft framing |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Site drainage installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Concrete foundation pouring |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | HVAC ductwork installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Interior wall framing |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Electrical conduit installation |  | 8 | 2024-05-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Fire sprinkler system installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Roof membrane installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Floor tile installation | 5 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Drywall installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Parking lot asphalt paving | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Landscape irrigation installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Structural steel erection | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Guardrail installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Exterior painting | 1 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Interior door installation | 7 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Window caulking and sealing | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Ceiling grid installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Building insulation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Hardwood flooring installation | 1.5 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Crown molding installation | 6.5 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Kitchen cabinetry installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Bathroom fixture installation | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Tool organization | 8 |  | 2024-05-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Team safety meeting | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Material delivery coordination | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Quality control inspection | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Stair railing installation | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Building permit processing | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Demolition work | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Scaffolding assembly | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Masonry wall construction | 5 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Plumbing rough-in | 3 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Exterior lighting installation | 3 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Rooftop HVAC unit installation | 5 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Subcontractor coordination | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Balcony waterproofing | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Emergency exit signage installation | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Project planning and scheduling | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Security system wiring | 8 |  | 2024-05-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Penthouse siding and coping | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Roof screen wall | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Commute to Site | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Garage Gutters | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Paperwork | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | L10 deck panels | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Column wraps @ podium | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Sheet metal roof @ L14 canopy | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Wall panels @ entry vestibule | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Penthouse gutters and DS | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Exterior window installation | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Basement waterproofing | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Elevator shaft framing | 8 |  | 2024-05-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MACDOU | Site drainage installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Concrete foundation pouring | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | HVAC ductwork installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Interior wall framing | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Electrical conduit installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Fire sprinkler system installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Roof membrane installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Floor tile installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Drywall installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Parking lot asphalt paving | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Landscape irrigation installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Structural steel erection | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Guardrail installation | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Exterior painting | 8 |  | 2024-04-30 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Interior door installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Window caulking and sealing | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Ceiling grid installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Building insulation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Hardwood flooring installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Crown molding installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Kitchen cabinetry installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Bathroom fixture installation | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Tool organization | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Team safety meeting | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Material delivery coordination | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Quality control inspection | 8 |  | 2024-04-29 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/6/2024 5:32:15 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BURAAR | Stair railing installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
MCNZAC | Building permit processing |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
TRACCO | Demolition work |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
UTLJOH | Scaffolding assembly |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Masonry wall construction |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Plumbing rough-in |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior lighting installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Rooftop HVAC unit installation |  | 6 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Subcontractor coordination |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Curtain wall installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Balcony waterproofing |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Emergency exit signage installation |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Project planning and scheduling |  | 8 | 2024-04-27 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Security system wiring | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Penthouse siding and coping | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Roof screen wall | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Commute to Site | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Garage Gutters | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Paperwork | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | L10 deck panels | 3 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Column wraps @ podium | 5 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Sheet metal roof @ L14 canopy | 3 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Wall panels @ entry vestibule | 5 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Penthouse gutters and DS | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 3 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Exterior window installation | 5 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Facade metal panel installation | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Basement waterproofing | 8 |  | 2024-04-26 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Elevator shaft framing | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Site drainage installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Concrete foundation pouring | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | HVAC ductwork installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Interior wall framing | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Electrical conduit installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Fire sprinkler system installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Roof membrane installation | 3 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Floor tile installation | 5 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Drywall installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Parking lot asphalt paving | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Landscape irrigation installation | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Structural steel erection | 8 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Guardrail installation | 6 |  | 2024-04-25 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Exterior painting | 2 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Interior door installation | 6 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Window caulking and sealing | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Ceiling grid installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Building insulation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Hardwood flooring installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Crown molding installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Kitchen cabinetry installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Bathroom fixture installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Tool organization | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Team safety meeting | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Material delivery coordination | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Quality control inspection | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Stair railing installation | 8 |  | 2024-04-24 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Building permit processing | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HANTYL | Demolition work | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Scaffolding assembly | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Masonry wall construction | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Plumbing rough-in | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior lighting installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Rooftop HVAC unit installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Subcontractor coordination | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Curtain wall installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Balcony waterproofing | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Emergency exit signage installation | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Project planning and scheduling | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Security system wiring | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Penthouse siding and coping | 8 |  | 2024-04-23 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Roof screen wall | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CUSCAR | Commute to Site | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
SLOKYL | Garage Gutters | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Paperwork | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | L10 deck panels | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Column wraps @ podium | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Wall panels @ entry vestibule | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Penthouse gutters and DS | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Exterior window installation | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Facade metal panel installation | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Basement waterproofing | 8 |  | 2024-04-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/29/2024 5:00:35 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
UTLJOH | Elevator shaft framing |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
COUMAR | Site drainage installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Concrete foundation pouring |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | HVAC ductwork installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Interior wall framing |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Electrical conduit installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Fire sprinkler system installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof membrane installation |  | 8 | 2024-04-20 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BLARYA | Floor tile installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Drywall installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Parking lot asphalt paving | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Landscape irrigation installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Structural steel erection | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Guardrail installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Exterior painting | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Interior door installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Window caulking and sealing | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Ceiling grid installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Building insulation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Hardwood flooring installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Crown molding installation | 8 |  | 2024-04-19 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BLARYA | Kitchen cabinetry installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Bathroom fixture installation | 5 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Tool organization | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Team safety meeting | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Material delivery coordination | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Quality control inspection | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Stair railing installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Building permit processing | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Demolition work | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Scaffolding assembly | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Masonry wall construction | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Plumbing rough-in | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Exterior lighting installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Rooftop HVAC unit installation | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Subcontractor coordination | 8 |  | 2024-04-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Curtain wall installation | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Balcony waterproofing | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Emergency exit signage installation | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Project planning and scheduling | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Security system wiring | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Penthouse siding and coping | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Roof screen wall | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Commute to Site | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Garage Gutters | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Paperwork | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | L10 deck panels | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Column wraps @ podium | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Wall panels @ entry vestibule | 8 |  | 2024-04-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Penthouse gutters and DS | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Exterior window installation | 6 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Facade metal panel installation | 1 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Basement waterproofing | 7 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Elevator shaft framing | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Site drainage installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Concrete foundation pouring | 5 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | HVAC ductwork installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Roof membrane installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Floor tile installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Drywall installation | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Parking lot asphalt paving | 8 |  | 2024-04-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Landscape irrigation installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Structural steel erection | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Guardrail installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Exterior painting | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Interior door installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Window caulking and sealing | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Ceiling grid installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Building insulation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Hardwood flooring installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Crown molding installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Kitchen cabinetry installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Bathroom fixture installation | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Tool organization | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Team safety meeting | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Material delivery coordination | 8 |  | 2024-04-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/21/2024 7:33:04 AM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Quality control inspection |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Stair railing installation |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Building permit processing |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Demolition work |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Scaffolding assembly |  | 6 | 2024-04-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Masonry wall construction | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Plumbing rough-in | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Exterior lighting installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Rooftop HVAC unit installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Subcontractor coordination | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Curtain wall installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Balcony waterproofing | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Emergency exit signage installation | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Project planning and scheduling | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Security system wiring | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Penthouse siding and coping | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Roof screen wall | 8 |  | 2024-04-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Commute to Site | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Garage Gutters | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Paperwork | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | L10 deck panels | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Column wraps @ podium | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Wall panels @ entry vestibule | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Penthouse gutters and DS | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Exterior window installation | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Facade metal panel installation | 8 |  | 2024-04-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Basement waterproofing | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Elevator shaft framing | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Site drainage installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Concrete foundation pouring | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | HVAC ductwork installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Interior wall framing | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Electrical conduit installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Fire sprinkler system installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Roof membrane installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Floor tile installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Drywall installation | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Parking lot asphalt paving | 2 |  | 2024-04-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Landscape irrigation installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Structural steel erection | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Guardrail installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Exterior painting | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Interior door installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Window caulking and sealing | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Ceiling grid installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building insulation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Hardwood flooring installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Crown molding installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Kitchen cabinetry installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Bathroom fixture installation | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Tool organization | 8 |  | 2024-04-09 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Team safety meeting | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Material delivery coordination | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Quality control inspection | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Stair railing installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Building permit processing | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Demolition work | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Scaffolding assembly | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Masonry wall construction | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Plumbing rough-in | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Exterior lighting installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Rooftop HVAC unit installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Subcontractor coordination | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Curtain wall installation | 8 |  | 2024-04-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/15/2024 3:22:49 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Balcony waterproofing | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Emergency exit signage installation | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Project planning and scheduling | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUITIT | Security system wiring | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Penthouse siding and coping | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Roof screen wall | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Commute to Site | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Garage Gutters | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Paperwork | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | L10 deck panels | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Column wraps @ podium | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Wall panels @ entry vestibule | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse gutters and DS | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Exterior window installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Facade metal panel installation | 6.5 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OTTJOH | Basement waterproofing | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Elevator shaft framing | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Site drainage installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Concrete foundation pouring | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | HVAC ductwork installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Interior wall framing | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Electrical conduit installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Fire sprinkler system installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Roof membrane installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Floor tile installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Drywall installation | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Parking lot asphalt paving | 8 |  | 2024-04-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HOYWES | Landscape irrigation installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Structural steel erection | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Guardrail installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Exterior painting | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Interior door installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Window caulking and sealing | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Ceiling grid installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Building insulation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Hardwood flooring installation | 1 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Crown molding installation | 7 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Kitchen cabinetry installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Bathroom fixture installation | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Tool organization | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Team safety meeting | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Material delivery coordination | 8 |  | 2024-04-03 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
HOYWES | Quality control inspection | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OETBRO | Stair railing installation | 7.5 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
QUINJR | Building permit processing | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Demolition work | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Scaffolding assembly | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Masonry wall construction | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | Plumbing rough-in | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Exterior lighting installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JAMNIC | Rooftop HVAC unit installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Subcontractor coordination | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Curtain wall installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Balcony waterproofing | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Emergency exit signage installation | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
OSBKEV | Project planning and scheduling | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Security system wiring | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAVJAM | Penthouse siding and coping | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Roof screen wall | 8 |  | 2024-04-02 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
LUCLAW | Commute to Site | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHBRI | Garage Gutters | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CATMAT | Paperwork | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BROAUS | L10 deck panels | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
BAUTHA | Column wraps @ podium | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
CAMPHI | Sheet metal roof @ L14 canopy | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
WISJER | Wall panels @ entry vestibule | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
STEJAC | Penthouse gutters and DS | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JACJOH | Sheet metal roof @ L14 canopy (roof build up) | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GRETAR | Exterior window installation | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
JOHSCO | Facade metal panel installation | 8 |  | 2024-04-01 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:4/6/2024 3:12:16 PM_Verified by:JOHNSON, SCOTT | 35 Stone |  |  | Uploaded
GROJER | Basement waterproofing | 2 |  | 2024-01-18 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/22/2024 2:26:08 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Elevator shaft framing | 2 |  | 2024-01-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/22/2024 2:26:08 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Site drainage installation | 4 |  | 2024-01-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/16/2024 10:47:45 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Concrete foundation pouring | 4.5 |  | 2024-01-04 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:1/8/2024 7:20:32 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | HVAC ductwork installation | 1 |  | 2023-12-11 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:12/15/2023 11:53:57 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Interior wall framing | 2 |  | 2023-12-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:12/8/2023 3:05:43 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Electrical conduit installation | 1.5 |  | 2023-12-07 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:12/8/2023 3:05:43 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
LUCLAW | Fire sprinkler system installation | 1.5 |  | 2023-10-13 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/16/2023 7:15:15 AM_Verified by:LUCAS, LAWRENCE | 35 Stone |  |  | Uploaded
LUCLAW | Roof membrane installation | 4 |  | 2023-10-12 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/16/2023 7:15:15 AM_Verified by:LUCAS, LAWRENCE | 35 Stone |  |  | Uploaded
LUCLAW | Floor tile installation | 1.5 |  | 2023-10-06 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/9/2023 6:53:46 AM_Verified by:LUCAS, LAWRENCE | 35 Stone |  |  | Uploaded
LUCLAW | Drywall installation | 4 |  | 2023-10-05 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:10/9/2023 6:53:46 AM_Verified by:LUCAS, LAWRENCE | 35 Stone |  |  | Uploaded
GROJER | Parking lot asphalt paving | 1 |  | 2023-06-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/26/2023 11:14:13 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Landscape irrigation installation | 2 |  | 2023-06-22 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/26/2023 11:14:13 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Structural steel erection | 1.5 |  | 2023-06-16 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/20/2023 7:57:08 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Guardrail installation | 1.5 |  | 2023-06-15 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:6/20/2023 7:57:08 AM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Exterior painting | 5 |  | 2023-05-17 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/22/2023 12:44:13 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Interior door installation | 2 |  | 2023-05-10 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/15/2023 1:41:11 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded
GROJER | Window caulking and sealing | 1.5 |  | 2023-05-08 | 6446 | Day_5-8 | JOHNSON, SCOTT | Verification:True_Verified at:5/15/2023 1:41:11 PM_Verified by:GROSS, JEREMY | 35 Stone |  |  | Uploaded